## tasks
Task id | Task type | Estimated duration | Task | Start | Duration
1 | Project Management | 26 weeks | Project management | 1 | 26
2 | Technical installation | 1 week | Installing test environment | 1 | 1
3 | Technical installation | 1 week | Installing production environment | 2 | 1
4 | Workshops | 1 week | Workshop 1 | 1 | 1
5 | Workshops | 1 week | Workshop 2 | 1 | 1
6 | Workshops | 1 week | Workshop 3 | 2 | 1
7 | Workshops | 1 week | Workshop 4 | 2 | 1
8 | Workshops | 1 week | Workshop 5 | 2 | 1
9 | Data input | 1 week | System Overview Training | 3 | 1
10 | Data input | 2 weeks | Data Collation | 3 | 2
11 | Data input | 2 weeks | More data input | 3 | 2
12 | Data input | 2 weeks | Insert all that is left | 3 | 2
13 | Data review | 1 week | Review data insertion | 5 | 1
14 | Interfaces | 1 week | Technical setup of interfaces | 6 | 1
15 | Interfaces | 3 weeks | Input interfaces | 6 | 3
16 | Interfaces | 1 week | Output interfaces | 8 | 1
17 | User training, part 1 | 1 week | Validate scope | 9 | 1
18 | User training, part 1 | 3 weeks | Train users | 9 | 3
19 | Module installations | 1 week | Module A | 12 | 1
20 | Module installations | 1 week | Module B | 12 | 1
21 | Module installations | 2 weeks | Module C | 12 | 2
22 | Module installations | 2 weeks | Review module installations and functionality | 12 | 2
23 | Process security and workflow | 1 week | Scope of security requirements workshop | 14 | 1
24 | Process security and workflow | 1 week | Defining and implementing security settings | 14 | 1
25 | Process security and workflow | 1 week | Process and workflow training | 14 | 1
26 | Setup monitoring | 1 week | Monitoring for input interfaces | 15 | 1
27 | Setup monitoring | 1 week | Monitoring for output interfaces | 15 | 1
28 | System preparation and UAT | 1 week | Preparing disaster recovery plan | 16 | 1
29 | System preparation and UAT | 1 week | Preparing test plan: UAT and system testing | 16 | 1
30 | System preparation and UAT | 1 week | Preparing training | 16 | 1
31 | System preparation and UAT | 1 week | Preparing support guide | 16 | 1
32 | System preparation and UAT | 2 weeks | User training | 16 | 2
33 | System preparation and UAT | 1 week | System testing | 17 | 1
34 | System preparation and UAT | 4 weeks | User testing | 17 | 4
35 | System preparation and UAT | 3 weeks | Enhancements raised by UAT | 18 | 3
36 | Data migration | 1 week | Insert dynamic data into system | 21 | 1
37 | Parallel run | 4 weeks | Use the system for a while before going live | 22 | 4
38 | System goes live | 4 weeks | FINALE | 22 | 4

## milestones
Task id | Task | Description | Milestone type | Start
13 | Review data insertion | Acceptance of static data | Control point | 6
16 | Output interfaces | Acceptance of interfaces | Control point | 9
22 | Review module installations and functionality | Acceptance of module installations | Control point | 14
25 | Process and workflow training | Acceptance of security and workflow procedure | Control point | 15
35 | Enhancements raised by UAT | Acceptance of system operability | Control point | 21
36 | Insert dynamic data into system | Acceptance of data migration | Control point | 22
38 | FINALE | System goes live | Project end | 26

## task_completion
Task id | Task type | Task | Responsible | Comments | Comment date | Category | Completion
1 | Project Management | Project management | Employee A |  |  | Actual | 40%
2 | Technical installation | Installing test environment | Employee B | Test environment ready with data minus interfaces | 2017-10-17 | Actual | 100%
3 | Technical installation | Installing production environment | Employee B | System installed, no data inserted | 2017-10-18 | Actual | 33%
4 | Workshops | Workshop 1 | Employee A | Separate notes in attachment A1 | 2017-10-20 | Actual | 100%
5 | Workshops | Workshop 2 | Employee A | Separate notes in attachment A2 | 2017-10-22 | Actual | 100%
6 | Workshops | Workshop 3 | Employee A | Separate notes in attachment A3 | 2017-10-24 | Actual | 100%
7 | Workshops | Workshop 4 | Employee A | Separate notes in attachment A4 | 2017-10-25 | Actual | 100%
8 | Workshops | Workshop 5 | Employee A | Separate notes in attachment A5 | 2017-10-28 | Actual | 100%
9 | Data input | System Overview Training | Employee B | Training the system to users fully when data insertion is completed. | 2017-10-30 | Actual | 33%
10 | Data input | Data Collation | Employee B | Initial data inserted. Doing the rest next week. | 2017-11-01 | Actual | 40%
11 | Data input | More data input | Employee B | Got bored, inserting more data in today already. | 2017-11-02 | Actual | 67%
12 | Data input | Insert all that is left | Employee B |  |  | Actual | 33%
13 | Data review | Review data insertion | Client | Details A were correct. | 2017-11-02 | Actual | 15%
14 | Interfaces | Technical setup of interfaces | Employee A |  |  | Actual
15 | Interfaces | Input interfaces | Employee A |  |  | Actual
16 | Interfaces | Output interfaces | Employee B |  |  | Actual
17 | User training, part 1 | Validate scope | Employee B |  |  | Actual
18 | User training, part 1 | Train users | Employee B |  |  | Actual
19 | Module installations | Module A |  |  |  | Actual
20 | Module installations | Module B |  |  |  | Actual
21 | Module installations | Module C |  |  |  | Actual
22 | Module installations | Review module installations and functionality |  |  |  | Actual
23 | Process security and workflow | Scope of security requirements workshop |  |  |  | Actual
24 | Process security and workflow | Defining and implementing security settings |  |  |  | Actual
25 | Process security and workflow | Process and workflow training |  |  |  | Actual
26 | Setup monitoring | Monitoring for input interfaces |  |  |  | Actual
27 | Setup monitoring | Monitoring for output interfaces |  |  |  | Actual
28 | System preparation and UAT | Preparing disaster recovery plan |  |  |  | Actual
29 | System preparation and UAT | Preparing test plan: UAT and system testing |  |  |  | Actual
30 | System preparation and UAT | Preparing training |  |  |  | Actual
31 | System preparation and UAT | Preparing support guide |  |  |  | Actual
32 | System preparation and UAT | User training |  |  |  | Actual
33 | System preparation and UAT | System testing |  |  |  | Actual
34 | System preparation and UAT | User testing |  |  |  | Actual
35 | System preparation and UAT | Enhancements raised by UAT |  |  |  | Actual
36 | Data migration | Insert dynamic data into system |  |  |  | Actual
37 | Parallel run | Use the system for a while before going live |  |  |  | Actual
38 | System goes live | FINALE |  |  |  | Actual
1 | Project Management | Project management | Employee A | 0 | 0 | Remaining | 60%
2 | Technical installation | Installing test environment | Employee B | Test environment ready with data minus interfaces | 2017-10-17 | Remaining | 0%
3 | Technical installation | Installing production environment | Employee B | System installed, no data inserted | 2017-10-18 | Remaining | 67%
4 | Workshops | Workshop 1 | Employee A | Separate notes in attachment A1 | 2017-10-20 | Remaining | 0%
5 | Workshops | Workshop 2 | Employee A | Separate notes in attachment A2 | 2017-10-22 | Remaining | 0%
6 | Workshops | Workshop 3 | Employee A | Separate notes in attachment A3 | 2017-10-24 | Remaining | 0%
7 | Workshops | Workshop 4 | Employee A | Separate notes in attachment A4 | 2017-10-25 | Remaining | 0%
8 | Workshops | Workshop 5 | Employee A | Separate notes in attachment A5 | 2017-10-28 | Remaining | 0%
9 | Data input | System Overview Training | Employee B | Training the system to users fully when data insertion is completed. | 2017-10-30 | Remaining | 67%
10 | Data input | Data Collation | Employee B | Initial data inserted. Doing the rest next week. | 2017-11-01 | Remaining | 60%
11 | Data input | More data input | Employee B | Got bored, inserting more data in today already. | 2017-11-02 | Remaining | 33%
12 | Data input | Insert all that is left | Employee B | 0 | 0 | Remaining | 67%
13 | Data review | Review data insertion | Client | Details A were correct. | 43041 | Remaining | 85%
14 | Interfaces | Technical setup of interfaces | Employee A | 0 | 0 | Remaining | 100%
15 | Interfaces | Input interfaces | Employee A | 0 | 0 | Remaining | 100%
16 | Interfaces | Output interfaces | Employee B | 0 | 0 | Remaining | 100%
17 | User training, part 1 | Validate scope | Employee B | 0 | 0 | Remaining | 100%
18 | User training, part 1 | Train users | Employee B | 0 | 0 | Remaining | 100%
19 | Module installations | Module A | 0 | 0 | 0 | Remaining | 100%
20 | Module installations | Module B | 0 | 0 | 0 | Remaining | 100%
21 | Module installations | Module C | 0 | 0 | 0 | Remaining | 100%
22 | Module installations | Review module installations and functionality | 0 | 0 | 0 | Remaining | 100%
23 | Process security and workflow | Scope of security requirements workshop | 0 | 0 | 0 | Remaining | 100%
24 | Process security and workflow | Defining and implementing security settings | 0 | 0 | 0 | Remaining | 100%
25 | Process security and workflow | Process and workflow training | 0 | 0 | 0 | Remaining | 100%
26 | Setup monitoring | Monitoring for input interfaces | 0 | 0 | 0 | Remaining | 100%
27 | Setup monitoring | Monitoring for output interfaces | 0 | 0 | 0 | Remaining | 100%
28 | System preparation and UAT | Preparing disaster recovery plan | 0 | 0 | 0 | Remaining | 100%
29 | System preparation and UAT | Preparing test plan: UAT and system testing | 0 | 0 | 0 | Remaining | 100%
30 | System preparation and UAT | Preparing training | 0 | 0 | 0 | Remaining | 100%
31 | System preparation and UAT | Preparing support guide | 0 | 0 | 0 | Remaining | 100%
32 | System preparation and UAT | User training | 0 | 0 | 0 | Remaining | 100%
33 | System preparation and UAT | System testing | 0 | 0 | 0 | Remaining | 100%
34 | System preparation and UAT | User testing | 0 | 0 | 0 | Remaining | 100%
35 | System preparation and UAT | Enhancements raised by UAT | 0 | 0 | 0 | Remaining | 100%
36 | Data migration | Insert dynamic data into system | 0 | 0 | 0 | Remaining | 100%
37 | Parallel run | Use the system for a while before going live | 0 | 0 | 0 | Remaining | 100%
38 | System goes live | FINALE | 0 | 0 | 0 | Remaining | 100%